## Chronology
version | build_id_or_constant | date_evidence | intent | headline_evidence | status
Scrapy concept | pre-v1.0 | 2026-08-24 (conversation) | Initial idea: Scrapy-based research crawler for nonprofit intelligence | No archive supplied; only referenced in conversation and v1.0 README | Evidence unavailable (no archive)
v1.0 | app/__init__.py 1.0.0; no RELEASE_METADATA | zip mtime 2026-08-24 (conversation session 1) | First runnable Flask web app + Scrapy crawler + SQLite history | 68 files, 31 app modules, 13 test files, 67 static test defs; lock without hashes; no auth token on web UI | Implemented but unverified (no machine-readable test result supplied)
v1.1 | 1.1.0 | 2026-08-24/25 (AUDIT_LOG v1.1 section) | Hardening: app/security.py (token, host/origin allow-list), crawler/resolver.py | FLAT archive root (no top folder); 74 files; +CSRF/CSP/SameSite/redirect/symlink controls (regex first-seen) | Implemented but unverified; 18/18 fail_on_v11_demo probes VULNERABLE (v1.2 evidence)
v1.2 | constant STILL 1.1.0 (identity defect) | 2026-08-25 (AUDIT_LOG v1.2 audit M1-M6/L1-L8) | Audit-driven hardening: app/net.py pinned transport, PSL, DNS-rebinding fix, deadlines, ZIP amplification guards | 87 files; ships generated data/history.sqlite3 and 6 reports (unexpected members); claim 211 tests on 3.11-3.14 later disproved (P0.D3 SyntaxError on 3.11); Scrapy TLS verification still off (P0-B) | Partially implemented; Linux 211 passed claim (no log supplied)
v2.0 Phase 0 | no archive (dev tree only) | 2026-08-25/26 (FINDINGS_RECONCILIATION, TASKS) | Backports/zstd, TLS verification for Scrapy, Windows console encoding (app/console.py), 3.11 syntax, wheel set | 454 tests x4 interpreters claimed; no archive or log supplied | Evidence unavailable (claims only)
v2.0-rc1 | 2.0.0; no RELEASE_METADATA | 2026-08-26 (Windows JSON 19:19 -0400) | Full re-architecture: app/engine/*, interfaces cli/restapi/webui/mcp/egress/service, evidence store, windows_acceptance_kit, 11 TLS fixture pems | 323 files, 94 modules, 61 test files; Windows: 2415 passed/1 failed/2 errors (Py 3.14.3), G5 FAIL, failing test ID lost to diagnostics flood (W5) | Failed (Windows acceptance all_pass=false); Linux 2417 claimed
v2.0-rc2 | 2.0.0 | 2026-08-26 (AUDIT_LOG W1-W5 section) | Windows remediation W1-W5 (encoding, env-size node ID, batch LF, kit capture, diagnostics flood) | 324 files; Windows kit 2427/0/0/0 all nine gates green (project claim, JSON not supplied) BUT launcher started legacy v1.2 app.webapp:8756 (code-confirmed) -> false positive | Failed at release level (W6-W9); kit result Evidence unavailable as JSON
v2.0-rc3 | 2.0.0 | 2026-08-26/27 (turn_0048 user paste) | W6-W9: launcher to app.interfaces.webui:8758, +engine/orchestrate.py, G8 runtime gate | 328 files; Windows (user paste): 2443 passed/1 failed/9 errors, G5 FAIL, G10 FAIL then attributed to pre-existing listener (V1-V4 kit defects) | Failed (all_pass=false); product path manually validated per owner
v2.0-rc4 | 2.0.0; build rc4-20260827T185542Z (a) and 185552Z (b) | 2026-08-27 | V1-V4 kit fixes, RELEASE_METADATA.json, scripts/build_release_zip.py | Two distinct rc4 builds ten seconds apart; (b) EMBEDS (a) as member --help/deborah-research-assistant-v2.0-rc4.zip (348 vs 347 files) = A-V21-1; NOT run on Windows | Implemented but unverified on Windows; packaging defect
v2.1-rc1 | 2.1.0; rc1-20260901T155054Z | 2026-09-01/02 (Windows JSON 2026-09-02) | Discovery/documents/jsrender, providers ats_boards/irs_teos/sec_edgar, pypdf; A-RC4 fixes | 364 files; Windows Py 3.12.6: junit 2571 tests/1 failure (test_post_redirect_refused ConnectionError), G5 FAIL, all_pass=false; PROJECT_STATUS self-contradiction about RC4 Windows acceptance | Failed (Windows all_pass=false); Linux 2571 claimed
v2.2-rc1 | 2.2.0; rc1-20260904T153111Z | 2026-09-04 (audit cycle 3) | UX/scenario work; superseded build 953d7cc4 shipped stale 2.1.0 constant (owner saw v2.1.0 on Windows); rebuilt c10c1722 | 374 files; byte-identical to 'Deborah Research Assistant (complete application).zip'; superseded archive NOT supplied; Linux 2668-2687 claimed | Implemented but unverified (Windows run showed wrong version; rebuilt archive not re-run on Windows)
v3.0-rc1 | 3.0.0; rc1-20260907T015406Z | 2026-09-06/07 (18 audit cycles; Windows JSON 2026-09-07) | Platform layer app/platform/*, docdiscovery/docingest/finmodel/pdfdoc/sourcetier, propublica provider, PDF/XLSX exports, SETUP.bat/START_APP.bat | 446 files; Linux 4191/0/0 (cycle 18, CLEAN); Windows Py 3.12.6: 4191 tests, 4178 passed/5 failed/7 errors/1 skipped; consent dialog always shown (screenshot) | Failed on Windows (W1-W9); Linux Implemented and verified for suite only
v3.0-rc2 | 3.0.0; rc2-20260907T080002Z | 2026-09-07 | W1-W9 Windows remediation, tests test_v30_rc2_w1..w9, RC2_FIX_REPORT, WINDOWS_REACCEPTANCE | 446 files (15 notes logs removed, 15 added); Linux 4308/0/0/0 on 3.13 and 3.14 claimed (logs in /tmp not supplied); Windows never re-run; A-RC2-1/A-RC2-2 audit findings | Implemented but unverified on Windows; Linux count Evidence unavailable as log
v3.1-rc1 | 3.1.0-dev; rc1-20260909T224424Z | 2026-09-09 | Gemini multimodal financial extraction (app/ai/geminiextract.py), consent + kill switch, in-document guard | 449 files; Linux 4371/0/0/0 on 3.13.12 and 3.14.3 (report; no log supplied); default model gemini-2.0-flash found retired live, changed to gemini-3.6-flash; real Hewlett PDF (2026-09-11) DOI-contaminated, no EIN | Implemented but unverified live at scale; real-use output failure
v3.2-rc1 | 3.2.0-dev; rc1-20260911T153938Z/155618Z/161010Z | 2026-09-11 | Keyless nonprofit pipeline app/engine/nonprofit.py + nonprofit_report.py, optional google-genai SDK transport, IRS BMF fallback | Three builds; final 448 files OMITS the 11 TLS fixture pems; full_suite 32 failed/4379 passed (build a), final_suite 2 failed/4411; live Hewlett HTTP 404 (name rewritten with 'and'); RESEARCH INCOMPLETE | Failed (acceptance failed; 2 test failures; package cannot reproduce suite)
v3.2-rc2 | constant still 3.2.0-dev; rc2-20260911T220332Z | 2026-09-11 (delivered 2026-09-15) | Six blockers: ampersand encoding, BMF fallback in production path, normalized profile, audited-statement reconciliation, two failing tests, pem packaging | 460 files; packaged suite 4426/0/0/0 Linux CPython 3.13.12 (junit supplied); live: ProPublica search 200 EIN 941655673, 12x XML 403 Cloudflare, IRS BMF/index_2025 timeout; identity NOT locked; Windows not run | Implemented and verified (Linux suite only); live acceptance Failed; Windows Not verified

## Features
feature | module(s) | v1.0 | v1.1 | v1.2 | v2.0-rc1 | v2.0-rc4 | v2.1-rc1 | v2.2-rc1 | v3.0-rc1 | v3.0-rc2 | v3.1-rc1 | v3.2-rc1 | v3.2-rc2
Web UI (Flask, loopback) | app/webapp.py -> app/interfaces/webui.py (v2.0+) | Implemented but unverified | Implemented but unverified | Implemented but unverified | Failed (RC1/RC2 launcher started legacy app.webapp) | Implemented but unverified | Implemented but unverified | Implemented but unverified (owner saw v2.1.0) | Failed on Windows (consent dialog) | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified
Scrapy crawler | app/crawler/* | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified
Pinned/SSRF-safe HTTP transport | app/net.py | Not present | Not present | Implemented but unverified | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Implemented and verified (live RC2 run used app.net)
Research modes (quick/deep) | app/engine/loop.py, orchestrate.py | Not present | Not present | Not present | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Failed (B-1 consent not bound to depth, fixed cycle 1) | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified
Entity resolution | app/engine/entity*.py, crawler/resolver.py | Not present | Partially implemented | Partially implemented | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Failed (Hewlett report DOI-contaminated) | Failed (404, no lock) | Failed (no lock: XML 403/timeouts)
Evidence store | app/engine/store*.py | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only
Source discovery / source tiers | app/engine/discovery*.py, sourcetier.py | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only
Document parsing / PDF text (pypdf, pdfplumber) | app/engine/documents.py, docingest.py, pdfdoc.py | Not present | Not present | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only
OCR (Tesseract, optional) | app/engine/documents.py | Not present | Not present | Not present | Not present | Not present | Partially implemented (optional binary, untested live) | Partially implemented | Partially implemented | Partially implemented | Partially implemented | Partially implemented | Partially implemented
Financial extraction model | app/engine/finmodel.py | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only
Form 990 / 990-PF via ProPublica | app/providers/propublica.py; app/engine/nonprofit.py (v3.2) | Not present | Not present | Not present | Partially implemented (regex hits only) | Partially implemented | Partially implemented | Partially implemented | Fixture-tested only | Fixture-tested only | Fixture-tested only | Failed live 404 | Partially implemented (search 200, XML 403)
IRS TEOS / EO BMF / 990 index | app/providers/irs_teos.py; nonprofit._bmf_discover | Not present | Not present | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only (offline only) | Failed live (timeouts; 2026 index 200)
Grants / money-flow | finmodel.py, nonprofit.normalized_profile | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only (0 live years)
Compensation / officers | nonprofit.normalized_profile | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Partially implemented | Partially implemented | Partially implemented | Fixture-tested only | Fixture-tested only
Gemini multimodal extraction (optional key) | app/ai/geminiextract.py; genai_transport.py (v3.2) | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Implemented but unverified (1 live call, 6/6 figures) | Implemented but unverified | Implemented but unverified
Audited-statement reconciliation | nonprofit.audit_reconciliation | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Fixture-tested only (0 live comparisons)
Report: Markdown/HTML/JSON | app/engine/report*.py; nonprofit_report.py | Implemented but unverified | Implemented but unverified | Implemented but unverified | Partially implemented (A-RC4-2 no HTML despite README) | Partially implemented | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented and verified (four files saved live) | Implemented and verified (four files saved live)
Report: PDF (reportlab) / XLSX (openpyxl) / CSV | app/platform/pdfreport.py, exports.py | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Failed Windows (W3/W4 PermissionError) | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified
History / comparison ('Research Since Last Run') | app/platform/runs.py, profiles.py | Partially implemented (sqlite history) | Partially implemented | Partially implemented | Partially implemented (A-RC4-5 silent drops) | Partially implemented | Partially implemented | Partially implemented | Implemented but unverified (W? history scope failed Windows) | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified
Meeting summary | no dedicated module found | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Not present
CLI | app/interfaces/cli.py | Not present | Not present | Not present | Implemented but unverified | Failed (A-RC4-1 start killed run; fixed v2.1) | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified
REST API | app/interfaces/restapi.py | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only
MCP server | app/interfaces/mcp.py | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only
Settings / provider diagnostics UI | webui.py /api/settings/*, providersettings | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Implemented but unverified | Implemented but unverified | Implemented but unverified | Failed (Brave wording test failed) | Implemented but unverified
Batch research from uploaded list | app/platform/intake.py | Not present | Not present | Not present | Not present | Not present | Not present | Not present | Implemented but unverified (M17-1 non-ASCII names) | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified
Archive/upload inspection (zip safety) | app/security.py zip checks | Partially implemented | Partially implemented | Implemented but unverified (M6 amplification) | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only
Windows setup / launchers | Start_Deborah_Research_Assistant.bat; SETUP.bat, START_APP.bat (v3.0+) | Implemented but unverified | Implemented but unverified | Failed (colorama missing P0.D2) | Failed (legacy target) | Implemented but unverified (not run) | Implemented but unverified | Implemented but unverified | Partially implemented (icacls W7 fix in RC2) | Implemented but unverified (not run) | Implemented but unverified | Implemented but unverified | Implemented but unverified
Windows acceptance kit | windows_acceptance_kit/* | Not present | Not present | Not present | Failed (8 gates, G5 fail) | Implemented but unverified (V1-V4 fixes, not run) | Failed (G5 fail) | Evidence unavailable | Failed (5F/7E/1S) | Implemented but unverified | Implemented but unverified | Implemented but unverified | Implemented but unverified
Egress consent gate | app/interfaces/egress.py (DEBORAH_INTERFACE_EGRESS) | Not present | Not present | Not present | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Fixture-tested only | Implemented and verified (live: start without consent refused) | Implemented and verified (live)

## Providers
provider | version_introduced | keyless_or_keyed | purpose | module | default_enabled | live_fixture_untested | env_var | limitations
Wikipedia | v1.0 | keyless | Encyclopaedic seed / tier-3 context | app/providers/wikipedia.py (v2.0+); crawler seeds (v1.x) | yes | Fixture-tested; live in v3.1 Hewlett run (tier 3 only) | - | AUDIT_V3: 'Wikipedia-heavy' results
Internet Archive | v1.0 | keyless | Archived copies of pages | app/providers/internet_archive.py | yes | Fixture-tested only | - | No live evidence supplied
GitHub | v1.0 | keyless (optional token) | Repository / org presence | app/providers/github.py | yes | Fixture-tested only | GITHUB_TOKEN (v2.0+) | Rate limits unmeasured
PyPI | v1.0 | keyless | Package presence | app/providers/pypi.py | yes | Fixture-tested only | - | Marginal relevance to nonprofits
OpenAlex | v1.0 | keyless | Scholarly works / affiliations | app/providers/openalex.py | yes | Fixture-tested only | - | Source of DOI contamination risk in v3.1 report (v3.1 PDF lists DOIs)
Crossref | v1.0 | keyless | DOI metadata | app/providers/crossref.py | yes | Fixture-tested only | - | Same as OpenAlex
Brave Search | v1.0 | keyed | Web search | app/providers/brave.py | off without key | Untested live | BRAVE_API_KEY | Free plan ended Feb 2026 per providersettings; recorded as paid
Tavily | v1.0 | keyed | Web search | app/providers/tavily.py | off without key | Untested live | TAVILY_API_KEY | No live evidence
Scrapy (bounded crawl) | v1.0 | keyless | Official-website crawling, sitemaps | app/crawler/* | yes | Fixture/offline; TLS verification OFF in v1.0-v1.2 (code-confirmed), True from v2.0 | - | P0-B
arXiv | v1.1 | keyless | Preprints | app/providers/arxiv.py | yes | Fixture-tested only | - | Marginal relevance
IRS (TEOS / EO BMF / 990 XML index) | v2.0-rc1 (regex); provider module irs_teos.py v2.1 | keyless | Authoritative EIN / exempt status / filing index | app/providers/irs_teos.py; app/engine/nonprofit._bmf_discover (v3.2) | yes | Live v3.2 RC2: eo_ca.csv TIMEOUT, index_2025 TIMEOUT, index_2026.csv 200 (47.5 MB) | - | Bulk-file body timeouts from sandbox; no per-object XML route
ProPublica Nonprofit Explorer | v2.0-rc1 (regex); app/providers/propublica.py v3.0 | keyless | 990 search, organization JSON, filing XML | app/providers/propublica.py; app/engine/nonprofit.py | yes | Live v3.2 RC1: 404 (and-rewrite); RC2: search 200, org 200, 12x download-xml 403 (Cloudflare challenge) | - | XML download blocked by Cloudflare; aggregator amounts never admitted
Wikidata | v2.0-rc1 | keyless | Entity identifiers | app/providers/wikidata.py | yes | Fixture-tested only | - | -
SEC EDGAR | v2.0-rc1 (regex); app/providers/sec_edgar.py v2.1 | keyless | Corporate filings | app/providers/sec_edgar.py | yes | Fixture-tested only | - | User-agent policy compliance not live-verified
Common Crawl | v2.0-rc1 | keyless | Index lookups | app/providers/commoncrawl.py | yes | Fixture-tested only | - | -
USAspending | v2.0-rc1 | keyless | Federal awards | app/providers/usaspending.py | yes | Fixture-tested only | - | -
ATS job boards | v2.1-rc1 | keyless | Public job postings | app/providers/ats_boards.py | yes | Fixture-tested only | - | -
Playwright (JS render) | v2.1-rc1 | keyless (local binary) | JS-rendered pages | app/engine/jsrender.py | off unless installed | Untested live | - | Optional dependency
Tesseract OCR | v2.1-rc1 | keyless (local binary) | Scanned PDFs | app/engine/documents.py | off unless installed | Untested live | - | Optional binary
Charity Navigator | v3.0-rc1 | keyless (tier list) | Source-tier classification only | app/engine/sourcetier.py | n/a | Fixture-tested only | - | Not a data fetcher
OpenCorporates | v3.0-rc1 | keyless (tier list) | Source-tier classification only | app/engine/sourcetier.py | n/a | Fixture-tested only | - | Not a data fetcher
Google Gemini | v3.1-rc1 | keyed | Multimodal financial extraction from PDFs | app/ai/geminiextract.py; app/ai/genai_transport.py (v3.2 optional SDK google-genai==2.22.0) | off (consent + key) | 1 live call 2026-09-09 (report); default gemini-2.0-flash was retired -> gemini-3.6-flash | GOOGLE_API_KEY / GEMINI_API_KEY; DEBORAH_GEMINI_MODEL | Free tier unmeasured; whole documents leave the computer; v3.1 metadata said 'no vendor SDK', v3.2 adds optional SDK
DuckDuckGo / OpenAI / Anthropic | tests only | - | Referenced in tests/settings labels only | tests/* | no | Not present as provider modules | - | Regex hits in tests only
Perplexity search | v3.2 (settings label) | keyed | Optional search | providersettings | off | Untested | PERPLEXITY_API_KEY (per UPGRADE_REPORT) | Not used in live runs

## Security
control | first_version | evidence | status_at_latest
Loopback-only bind with override refusal | v1.0 (127.0.0.1); explicit refusal + DEBORAH_ALLOW_NONLOCAL v2.0+ | webui.main() code-confirmed v3.2-rc2 | Implemented and verified (code)
Bootstrap secret / session auth | v1.1 (token_ok, request_token) | v1.2 L7: token in URLs/logs; v2.0+ fragment #bs= | Implemented and verified (code; live RC2: anonymous settings refused)
CSRF token header | v1.1 | security.csrf_header_ok; live RC2: CSRF-less start 403 | Implemented and verified (live)
Host / Origin allow-list | v1.1 host_allowed/origin_allowed; v1.2 origin | webui.py: Origin checked against _expected_origins | Implemented and verified (code)
CSP script-src 'self', no inline | v1.1 | _harden after_request; CSP_UI | Implemented and verified (code)
X-Frame-Options DENY, nosniff, no-referrer, no-store | v1.1/v1.2 | _harden | Implemented and verified (code)
SameSite=Strict cookie, HttpOnly | v1.1 | webui.py:5043 | Implemented and verified (code)
SSRF: public-IP admission + IP pinning + DNS-rebinding defence | v1.0 partial; v1.2 M1 fix (app/net.py) | net._open_pinned_socket; MAX_REDIRECTS=3 | Fixture-tested only + live RC2 transport
TLS verification (stdlib transport) | v1.2 app/net.py | ssl.create_default_context() | Implemented and verified (code); negative fixtures absent from v3.2-rc1 zip
TLS verification (Scrapy) | v2.0 Phase 0 (P0-B) | settings.py DOWNLOAD_VERIFY_CERTIFICATES True; absent in v1.0-v1.2 | Implemented and verified (code); v1.0-v1.2 Failed
Proxy environment ignored | v2.0 N9 open -> fixed by v2.0 RCs | net.py docstring + code: never consults HTTP_PROXY | Implemented and verified (code)
Response byte ceilings / deadlines | v1.2 M2/M3 | MAX_RESPONSE_BYTES=2_000_000; budget | Fixture-tested only
Upload / ZIP safety (traversal, amplification, case collisions) | v1.0 basic; v1.2 M6 | test_zip_safety_rejects_case_collisions | Fixture-tested only
Egress consent gate | v2.0-rc1 | egress.py ENV_ALLOW_EGRESS | Implemented and verified (live RC2)
Consent bound to research depth | v3.0 cycle 1 B-1 (defect) | fixed cycle 1 fix report | Implemented but unverified (fix jsdom/HTTP tests)
Consent dialog hidden until needed | v3.0-rc1 W8 defect (always painted) | _HIDDEN_RULE + import-time assert (RC2) | Fixture-tested only (jsdom only; no real-browser evidence after fix)
Secret redaction in logs/excerpts | v1.2 | nonprofit.py digit-run redaction; header deny-list in net.py | Fixture-tested only
Prompt-injection flags | v1.2 (regex); J-V21-1 flags not rendered | fixed v2.1/v2.2 per ledger | Fixture-tested only
Rate limiting (per-IP token bucket) | v1.1 (allow()) | _limiter.allow() -> 429 | Fixture-tested only
Restrictive file permissions (keys, DB) | v2.0 | W7: chmod no-op on Windows -> icacls in RC2 | Implemented but unverified (Windows unverified)
Hash-locked dependencies | v1.1 (lock hashes) | requirements.lock sha e2da018d frozen v3.0-v3.2 | Implemented and verified (manifest)
Release identity from archive contents | v2.0-rc4 RELEASE_METADATA | v3.2-rc2 constant 3.2.0-dev / README rc1-only | Partially implemented (identity inconsistency in latest)

## Tests
version_or_run | platform | python | tests | passed | failed | errors | skipped | source | evidence_type | notes
v1.2 | Linux | 3.14.3 | 211 | 211 | 0 | 0 | 0 | AUDIT_LOG.md (claim) | project claim | no log supplied; P0.D3 shows 3.11 never ran
v1.2 probes on v1.1 | Linux | - | 18 probes | 0 | 18 VULNERABLE | - | - | fail_on_v11_demo.py (claim in AUDIT_LOG) | project claim | red proof that v1.1 was vulnerable
v2.0 Phase 0 | Linux | 3.11/3.12/3.13/3.14 | 454 x4 | 454 x4 | 0 | 0 | 0 | TASKS/FINDINGS_RECONCILIATION | project claim | no log
v2.0-rc1 | Linux | - | 2417 | 2417 | 0 | 0 | 0 | AUDIT_LOG.md | project claim | -
v2.0-rc1 | Windows 11 26200 | 3.14.3 | 2418 | 2415 | 1 | 2 | 0 | uploaded 8830b1d4.../windows_acceptance_result.json 2026-08-26 19:19 -0400 | machine-readable | G5 FAIL; all_pass false; failing test ID unavailable (diagnostics flood)
v2.0-rc2 | Linux | - | 2427 | 2427 | 0 | 0 | 0 | AUDIT_LOG.md | project claim | -
v2.0-rc2 | Windows 11 | - | 2427 | 2427 | 0 | 0 | 0 | owner-reported per AUDIT_LOG (JSON not supplied) | project claim | all nine gates green but launcher ran legacy app -> false positive
v2.0-rc3 | Linux | - | 2490/2499/2502 | - | 0 | 0 | 0 | notes/mutation-log-rc* | project claim | successive counts during rc3
v2.0-rc3 | Windows 11 | 3.14 (wrapper) | 2453 | 2443 | 1 | 9 | 0 | turn_0048 user paste (no JSON) | conversation | G5 FAIL, G10 FAIL (pre-existing listener); all_pass false
v2.0-rc3 kit run on rc2 zip | Linux | - | 15 | 1 | 14 | 0 | 0 | notes rc3 log | project log | gate red-proof
v2.0-rc4 packaged tests on rc3 zip | Linux | - | 20 | 2 | 0 | 18 | 0 | notes rc4 log | project log | red-proof
v2.0-rc4 | Windows | - | - | - | - | - | - | - | Evidence unavailable | RC4 never run on Windows (PROJECT_STATUS contradiction)
v2.1-rc1 | Linux | - | 2571 | 2571 | 0 | 0 | 0 | AUDIT_LOG.md | project claim | -
v2.1-rc1 | Windows | 3.12.6 | 2571 | 2570 | 1 | 0 | 0 | uploaded 0c084c0f.../acceptance_junit.xml 2026-09-02 | machine-readable | test_audit_regressions.py::test_post_redirect_refused ConnectionError; G5 FAIL; all_pass false
v2.2-rc1 | Linux | - | 2668 dev / 2686-2687 with archive | all | 0 | 0 | 0 | AUDIT_LOG.md cycle 3 | project claim | -
v2.2-rc1 | Windows | 3.14 (Start_Deborah_Python314.bat) | - | - | - | - | - | owner screenshot (UI showed v2.1.0) | conversation/screenshot | no suite run; version defect
v3.0 audit cycle 1 | Linux | 3.13 | 3637 | 3637 | 0 | 0 | 0 | v30/audit1_pytest.log | log on disk | -
v3.0 cycle 16 | Linux | 3.13/3.14 | 4146 | 4146 | 0 | 0 | 0 | v30/AUDIT_CYCLE_16.md | project claim (4 runs) | -
v3.0 interim kit run | Linux | 3.14.3 | 4103 | 4103 | 0 | 0 | 0 | v30/deborah-research-engine-v3.0/windows_acceptance_kit/* 2026-09-06 | log on disk | G2/G9 fail on Linux by design
v3.0-rc1 final | Linux | 3.13 and 3.14 | 4191 | 4191 | 0 | 0 | 0 | v30/AUDIT_CYCLE_18.md; HANDOFF_TO_AKSHAY.md | project claim (4 runs) | cycle 18 CLEAN
v3.0-rc1 | Windows | 3.12.6 | 4191 | 4178 | 5 | 7 | 1 | uploaded eed77b4f.../acceptance_junit.xml 2026-09-07 | machine-readable | test_v21_packaging stray archives; history_store_scope; cycle9_exports [xlsx],[json]; test_v30_sbom; 7 errors screen_timestamps; all_pass false
v3.0-rc2 red proofs | Linux | 3.13 | W1 18, W2 7, W34 12, W5 10, W6 29, W7 14, W8 21, W9 6 | 3/6/2/7/27/6/12/5 | 15/1/10/3/2/8/9/1 | 0 | 0 | v30/rc2_dev/proofs_rc1_w*.log | log on disk | tests fail on rc1 tree as intended
v3.0-rc2 | Linux | 3.13.12 and 3.14.3 | 4308 | 4308 | 0 | 0 | 0 | RC2_FIX_REPORT.md (logs in /tmp not supplied) | project claim | -
v3.0-rc2 | Windows | - | - | - | - | - | - | - | Evidence unavailable | never run
v3.1-rc1 baseline (rc2 tree) | Linux | 3.13.12 | 4308 | 4308 | 0 | 0 | 0 | V31_FEATURE_REPORT.md | project claim | -
v3.1-rc1 | Linux | 3.13.12 and 3.14.3 | 4371 | 4371 | 0 | 0 | 0 | V31_FEATURE_REPORT.md | project claim | 1 failure when run concurrently (A-RC2-2 residual)
v3.1-rc1 | Windows | - | - | - | - | - | - | - | Evidence unavailable | never run
v3.2-rc1 full suite (build a) | Linux | 3.13.12 | 4411 | 4379 | 32 | 0 | 0 | v32/evidence/full_suite.log/.xml | log on disk | -
v3.2-rc1 final suite (source tree) | Linux | 3.13.12 | 4413 | 4411 | 2 | 0 | 0 | v32/evidence/final_suite.log/.xml | log on disk | test_w1_every_text_operation_states_its_encoding; test_brave_is_recorded_as_paid...; ran source tree not zip
v3.2-rc1 live acceptance | Linux | 3.13.12 | 1 run | 0 | 1 | 0 | 0 | v32/evidence/live_acceptance.json | machine-readable | ProPublica 404; RESEARCH INCOMPLETE
v3.2-rc2 packaged suite | Linux | 3.13.12 | 4426 | 4426 | 0 | 0 | 0 | v32/deliverables_rc2/packaged_suite_rc2_junit.xml (388.97 s) | machine-readable | extracted rc2 tree
v3.2-rc2 live acceptance | Linux | 3.13.12 | 1 run | 0 | 1 | 0 | 0 | v32/deliverables_rc2/live_acceptance_rc2.json | machine-readable | search 200; 12x XML 403; IRS timeouts; identity NOT locked
v3.2-rc2 | Windows | - | - | - | - | - | - | - | Evidence unavailable | never run

## Archives
filename | path | assigned_version | release_candidate | byte_size | file_count | sha256 | internal_root_folder | single_root | tls_fixture_pems | db_files_shipped | key_or_pem_outside_tests | release_metadata | byte_identical_duplicate_of | packaging_notes | name_vs_content
Deborah Research Assistant (complete application).zip | Deborah Research Assistant (complete application).zip | v2.2-rc1 | 1 | 1791835 | 374 | c10c1722de4de77292d843f9ffd7d6c9573065b916d5234efb10f329ff5c77ec | deborah-research-engine-v2.2 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260904T153111Z; |  |  | generic name; content = v2.2-rc1 c10c1722
deborah-research-assistant-v1.1.zip | deborah-research-assistant-v1.1.zip | v1.1 | none (v1.x had no RC numbering) | 325692 | 74 | 0c4dd33fece35ea1299672f932ebc10613eede11c547b2ad440565e990d0c641 | .env.example;.gitignore;ARCHITECTURE.md;AUDIT_LOG.md;PROJECT_STATUS.md;QUICK_STA | False | 0 |  |  |  |  | FLAT root (no top-level folder) | matches
deborah-research-assistant-v1.2.zip | deborah-research-assistant-v1.2.zip | v1.2 | none (v1.x had no RC numbering) | 397997 | 87 | bc3112569aa066834016c6fbc9239bda47280453aeb547ad86c5fad5d061a055 | deborah-research-assistant-v1.2 | True | 0 | deborah-research-assistant-v1.2/data/history.sqlite3 |  |  |  | ships runtime DB: deborah-research-assistant-v1.2/data/history.sqlite3 | MISMATCH: constant 1.1.0
deborah-research-assistant-v2.0-rc1.zip | deborah-research-assistant-v2.0-rc1.zip | v2.0-rc1 | 1 | 1588230 | 323 | 5d63e097d645280bacfac1fa5c46703b6de8b5415be33622731b88c6494529a2 | deborah-research-engine-v2.0 | True | 11 | [5 empty] | matches
deborah-research-assistant-v2.0-rc2.zip | deborah-research-assistant-v2.0-rc2.zip | v2.0-rc2 | 2 | 1601401 | 324 | f00f33959ca75493489c9c647e53198806cadec0d2b130d34b9b6c4b57d5779a | deborah-research-engine-v2.0 | True | 11 | [5 empty] | matches
deborah-research-assistant-v2.0-rc3.zip | deborah-research-assistant-v2.0-rc3.zip | v2.0-rc3 | 3 | 1621192 | 328 | 0d36c0c66c0b60f1377e83b5757cbdb6572f96583ca3a18263fae4a7cc02cf93 | deborah-research-engine-v2.0 | True | 11 | [5 empty] | matches
deborah-research-assistant-v2.0-rc4.zip | deborah-research-assistant-v2.0-rc4.zip | v2.0-rc4(b-185552Z) | 4 | 3309667 | 348 | 976814d7905f37212516c02c209f440f7f33356f416ec275afa81e562c8dedea | deborah-research-engine-v2.0 | True | 11 |  |  | release_candidate=4;build_id=rc4-20260827T185552Z; |  | embeds nested rc4 zip member | matches
deborah-research-assistant.zip | deborah-research-assistant.zip | v1.0 | none (v1.x had no RC numbering) | 128889 | 68 | 5661d6a78d9c9f623f0f3085e9f03e9162ef04ba37ea7836013a8e803bf55b29 | deborah-research-assistant | True | 0 | [5 empty] | matches
deborah-research-assistant-v2.0-rc4.zip | rc4/deborah-research-engine-v2.0/--help/deborah-research-assistant-v2.0-rc4.zip | v2.0-rc4(a-185542Z) | 4 | 1677720 | 347 | e69cf9be888aa2c6e90ad5f9718210bacf90fc695e78ecf31f2b23de00e71575 | deborah-research-engine-v2.0 | True | 11 |  |  | release_candidate=4;build_id=rc4-20260827T185542Z; |  |  | matches
deborah-research-assistant-v2.1-rc1.zip | v21/deborah-research-assistant-v2.1-rc1.zip | v2.1-rc1 | 1 | 1735522 | 364 | 2e55a25faf4d2f09b27ee201bb1cc6d6d0a3135f81d6ee0ca664730a64f6c7f3 | deborah-research-engine-v2.1 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260901T155054Z; |  |  | matches
deborah-research-assistant-v2.2-rc1.zip | v22/dist/deborah-research-assistant-v2.2-rc1.zip | v2.2-rc1 | 1 | 1791835 | 374 | c10c1722de4de77292d843f9ffd7d6c9573065b916d5234efb10f329ff5c77ec | deborah-research-engine-v2.2 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260904T153111Z; | Deborah Research Assistant (complete application).zip | byte-identical duplicate | matches
deborah-research-assistant-v3.0-rc1.zip | v30/deborah-research-assistant-v3.0-rc1.zip | v3.0-rc1 | 1 | 5708067 | 446 | 1fddc2d97f8693e78ebb026bc9bf479fc7c96147e3bb63a3892d9a77a0a81626 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260907T015406Z; |  |  | matches
deborah-research-assistant-v3.0-rc1.PRE-CYCLE17-FIX-DIST-2026-09-07T0135Z.zip | v30/dist/deborah-research-assistant-v3.0-rc1.PRE-CYCLE17-FIX-DIST-2026-09-07T0135Z.zip | v3.0-rc1 interim (PRE-CYCLE17-FIX-DIST-2026-09-07T0135Z) | 1 | 5689000 | 445 | b3bb2d9efef2e67c2b034a261b19fb197369218fab053a92d7746939c77cad60 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T230802Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-LOGENTRY-DIST-2026-09-07T0150Z.zip | v30/dist/deborah-research-assistant-v3.0-rc1.PRE-LOGENTRY-DIST-2026-09-07T0150Z.zip | v3.0-rc1 interim (PRE-LOGENTRY-DIST-2026-09-07T0150Z) | 1 | 5705224 | 446 | 8db69e1bb3bb1338ef09dcd27ad7071ccaee17c7250852b28042946b6fc9ab30 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260907T013536Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.zip | v30/dist/deborah-research-assistant-v3.0-rc1.zip | v3.0-rc1 | 1 | 5708067 | 446 | 1fddc2d97f8693e78ebb026bc9bf479fc7c96147e3bb63a3892d9a77a0a81626 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260907T015406Z; | v30/deborah-research-assistant-v3.0-rc1.zip | byte-identical duplicate | matches
deborah-research-assistant-v3.0-rc2.zip | v30/rc2_dev/dist/deborah-research-assistant-v3.0-rc2.zip | v3.0-rc2 | 2 | 5758354 | 446 | 4d8f1dfc02e85850cd6a3813b75d55298d63fe3ffc374099f056398017726274 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=2;build_id=rc2-20260907T080002Z; |  |  | matches
deborah-research-assistant-v3.0-rc1-cycle3-20260905T230414Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1-cycle3-20260905T230414Z.zip | v3.0-rc1 interim (unnamed) | 1 | 2281035 | 420 | 270307c6d2460d9897533479e921af8bf896eb030f8a2b49ec8718c488ece805 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T230414Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.CYCLE9-INTERIM-BEFORE-BUILDLOG-2026-09-06T0709Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.CYCLE9-INTERIM-BEFORE-BUILDLOG-2026-09-06T0709Z.zip | v3.0-rc1 interim (CYCLE9-INTERIM-BEFORE-BUILDLOG-2026-09-06T0709Z) | 1 | 5585482 | 432 | 163536798ebdd099d10bfb1251fdea3c39705ee4b7086fae06753147cbfd86fb | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T070606Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.CYCLE9-INTERIM-BEFORE-BUILDLOG-DIST-2026-09-06T0709Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.CYCLE9-INTERIM-BEFORE-BUILDLOG-DIST-2026-09-06T0709Z.zip | v3.0-rc1 interim (CYCLE9-INTERIM-BEFORE-BUILDLOG-DIST-2026-09-06T0709Z) | 1 | 5585482 | 432 | 163536798ebdd099d10bfb1251fdea3c39705ee4b7086fae06753147cbfd86fb | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T070606Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.CYCLE9-INTERIM-BEFORE-BUILDLOG-2026-09-06T0709Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.INTERIM-CYCLE13-20260906T182040Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.INTERIM-CYCLE13-20260906T182040Z.zip | v3.0-rc1 interim (INTERIM-CYCLE13-20260906T182040Z) | 1 | 5657521 | 442 | 2eea019f44247f38576cc4a5948e4fc722773a505da22b9cf472872bbae2ff29 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T175925Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.INTERMEDIATE-2026-09-05T2206Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.INTERMEDIATE-2026-09-05T2206Z.zip | v3.0-rc1 interim (INTERMEDIATE-2026-09-05T2206Z) | 1 | 2264786 | 418 | 691f2677f08f2c7ce9bac7968a089ebb493f9f63395f61dad9b6d8946fd1ecbd | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T220552Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.INTERMEDIATE-2026-09-05T2254Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.INTERMEDIATE-2026-09-05T2254Z.zip | v3.0-rc1 interim (INTERMEDIATE-2026-09-05T2254Z) | 1 | 2277494 | 420 | 8f61e73becebf43b81b716f333deaf6d54bf3027ce4617b4f3362d9064df7f41 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T225328Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.INTERMEDIATE-cycle4-2026-09-06T0011Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.INTERMEDIATE-cycle4-2026-09-06T0011Z.zip | v3.0-rc1 interim (INTERMEDIATE-cycle4-2026-09-06T0011Z) | 1 | 2292613 | 420 | d808d9f3e4c74eced416607f45a727637db641d4c888bdc2bb253171e27b6cf3 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T000744Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-BUILDLOG-2026-09-05T2200Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-BUILDLOG-2026-09-05T2200Z.zip | v3.0-rc1 interim (PRE-BUILDLOG-2026-09-05T2200Z) | 1 | 2261851 | 418 | ba1f62f101eb563e09aaa2bef8c4d2b00e253f038be64f9a2a755909e0cf4bf2 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T220012Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-BUILDLOG-2026-09-05T2304Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-BUILDLOG-2026-09-05T2304Z.zip | v3.0-rc1 interim (PRE-BUILDLOG-2026-09-05T2304Z) | 1 | 2277578 | 420 | 5b850afe19b79a69720e37a4e8925657dcd5e9627b3a55300c510f15d7252f8c | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T225427Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE10-FIX-2026-09-06T0927Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE10-FIX-2026-09-06T0927Z.zip | v3.0-rc1 interim (PRE-CYCLE10-FIX-2026-09-06T0927Z) | 1 | 5588335 | 432 | 1e117cdcc9b1ed941f7bb075820a571cd6e620a08843814fd586b460897b452d | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T070922Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE10-FIX-DIST-2026-09-06T0927Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE10-FIX-DIST-2026-09-06T0927Z.zip | v3.0-rc1 interim (PRE-CYCLE10-FIX-DIST-2026-09-06T0927Z) | 1 | 5588335 | 432 | 1e117cdcc9b1ed941f7bb075820a571cd6e620a08843814fd586b460897b452d | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T070922Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE10-FIX-2026-09-06T0927Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE11-FIX-20260906T115818Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE11-FIX-20260906T115818Z.zip | v3.0-rc1 interim (PRE-CYCLE11-FIX-20260906T115818Z) | 1 | 5611548 | 436 | 7b391712da8aa749988f2bea45d71f00ac502634eafa1448e140fb1ecb64efe6 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T094026Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE11-FIX-DIST-20260906T115818Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE11-FIX-DIST-20260906T115818Z.zip | v3.0-rc1 interim (PRE-CYCLE11-FIX-DIST-20260906T115818Z) | 1 | 5611548 | 436 | 7b391712da8aa749988f2bea45d71f00ac502634eafa1448e140fb1ecb64efe6 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T094026Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE11-FIX-20260906T115818Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE12-FIX-20260906T152143Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE12-FIX-20260906T152143Z.zip | v3.0-rc1 interim (PRE-CYCLE12-FIX-20260906T152143Z) | 1 | 5644101 | 442 | f7b9638640ad55f87baf4a224012b9c38f7a73e6e84ea5235f549d6dec57db2a | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T130258Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE12-FIX-DIST-20260906T152143Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE12-FIX-DIST-20260906T152143Z.zip | v3.0-rc1 interim (PRE-CYCLE12-FIX-DIST-20260906T152143Z) | 1 | 5644101 | 442 | f7b9638640ad55f87baf4a224012b9c38f7a73e6e84ea5235f549d6dec57db2a | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T130258Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE12-FIX-20260906T152143Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE13-FIX-20260906T175916Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE13-FIX-20260906T175916Z.zip | v3.0-rc1 interim (PRE-CYCLE13-FIX-20260906T175916Z) | 1 | 5651135 | 442 | 573d002a888f42b01ef5e3979f26f68d405906fee314cdd5a40e3b1c378cd753 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T152200Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE13-FIX-DIST-20260906T175916Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE13-FIX-DIST-20260906T175916Z.zip | v3.0-rc1 interim (PRE-CYCLE13-FIX-DIST-20260906T175916Z) | 1 | 5651135 | 442 | 573d002a888f42b01ef5e3979f26f68d405906fee314cdd5a40e3b1c378cd753 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T152200Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE13-FIX-20260906T175916Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE14-FIX-2026-09-06T2106Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE14-FIX-2026-09-06T2106Z.zip | v3.0-rc1 interim (PRE-CYCLE14-FIX-2026-09-06T2106Z) | 1 | 5660865 | 442 | ea5eeded48d1a8aed565483fe554f48357d0791f9b9f7223a2593f82890dc12c | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T182040Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE14-FIX-DIST-2026-09-06T2106Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE14-FIX-DIST-2026-09-06T2106Z.zip | v3.0-rc1 interim (PRE-CYCLE14-FIX-DIST-2026-09-06T2106Z) | 1 | 5660865 | 442 | ea5eeded48d1a8aed565483fe554f48357d0791f9b9f7223a2593f82890dc12c | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T182040Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE14-FIX-2026-09-06T2106Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE15-FIX-20260906T223313Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE15-FIX-20260906T223313Z.zip | v3.0-rc1 interim (PRE-CYCLE15-FIX-20260906T223313Z) | 1 | 5680808 | 445 | 33f35379ce3023fcea329654b23cdbda05ebb11b94613af50a49d6e6ac0e6363 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T211428Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE15-FIX-DIST-20260906T223313Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE15-FIX-DIST-20260906T223313Z.zip | v3.0-rc1 interim (PRE-CYCLE15-FIX-DIST-20260906T223313Z) | 1 | 5680808 | 445 | 33f35379ce3023fcea329654b23cdbda05ebb11b94613af50a49d6e6ac0e6363 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T211428Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE15-FIX-20260906T223313Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE17-FIX-2026-09-07T0135Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE17-FIX-2026-09-07T0135Z.zip | v3.0-rc1 interim (PRE-CYCLE17-FIX-2026-09-07T0135Z) | 1 | 5689000 | 445 | b3bb2d9efef2e67c2b034a261b19fb197369218fab053a92d7746939c77cad60 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T230802Z; | v30/dist/deborah-research-assistant-v3.0-rc1.PRE-CYCLE17-FIX-DIST-2026-09-07T0135Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE17-FIX-DIST-2026-09-07T0135Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE17-FIX-DIST-2026-09-07T0135Z.zip | v3.0-rc1 interim (PRE-CYCLE17-FIX-DIST-2026-09-07T0135Z) | 1 | 5689000 | 445 | b3bb2d9efef2e67c2b034a261b19fb197369218fab053a92d7746939c77cad60 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T230802Z; | v30/dist/deborah-research-assistant-v3.0-rc1.PRE-CYCLE17-FIX-DIST-2026-09-07T0135Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE2-FIX-2026-09-05T1932Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE2-FIX-2026-09-05T1932Z.zip | v3.0-rc1 interim (PRE-CYCLE2-FIX-2026-09-05T1932Z) | 1 | 2209986 | 414 | 1b305100ed57dcee80a183750ac9ddf855546dea8973317640203b9dc956d70e | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T193206Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE2-FIX-2026-09-05T2000Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE2-FIX-2026-09-05T2000Z.zip | v3.0-rc1 interim (PRE-CYCLE2-FIX-2026-09-05T2000Z) | 1 | 2213791 | 414 | f6200fd93df1adf7574de52332305017188763f04041ea27f1d9dde63c0c281d | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T200026Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE3-FIX-2026-09-05T2253Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE3-FIX-2026-09-05T2253Z.zip | v3.0-rc1 interim (PRE-CYCLE3-FIX-2026-09-05T2253Z) | 1 | 2264919 | 418 | c427339ebb516f87760dc2f1009c498f64456b76d4ef3307edf93c0ba47b989a | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T220624Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE3-FIX-DIST-2026-09-05T2253Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE3-FIX-DIST-2026-09-05T2253Z.zip | v3.0-rc1 interim (PRE-CYCLE3-FIX-DIST-2026-09-05T2253Z) | 1 | 2264919 | 418 | c427339ebb516f87760dc2f1009c498f64456b76d4ef3307edf93c0ba47b989a | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T220624Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE3-FIX-2026-09-05T2253Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE4-FIX-2026-09-06T0011Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE4-FIX-2026-09-06T0011Z.zip | v3.0-rc1 interim (PRE-CYCLE4-FIX-2026-09-06T0011Z) | 1 | 2281035 | 420 | 270307c6d2460d9897533479e921af8bf896eb030f8a2b49ec8718c488ece805 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T230414Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1-cycle3-20260905T230414Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE5-FIX-2026-09-06T0117Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE5-FIX-2026-09-06T0117Z.zip | v3.0-rc1 interim (PRE-CYCLE5-FIX-2026-09-06T0117Z) | 1 | 2292640 | 420 | 9be087216c785f3b767ae0655c25cbe806c8d592ec8b910b6366bf23c6888887 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T000758Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE5-FIX-DIST-2026-09-06T0117Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE5-FIX-DIST-2026-09-06T0117Z.zip | v3.0-rc1 interim (PRE-CYCLE5-FIX-DIST-2026-09-06T0117Z) | 1 | 2292640 | 420 | 9be087216c785f3b767ae0655c25cbe806c8d592ec8b910b6366bf23c6888887 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T000758Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE5-FIX-2026-09-06T0117Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE6-FIX-20260906T021626Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE6-FIX-20260906T021626Z.zip | v3.0-rc1 interim (PRE-CYCLE6-FIX-20260906T021626Z) | 1 | 5527900 | 428 | 0659232d6c55ba274f2d0d2f0499bc72bd325369ce89ca3f95c0f33d95bd8a3b | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T011745Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE6-FIX-DIST-20260906T021626Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE6-FIX-DIST-20260906T021626Z.zip | v3.0-rc1 interim (PRE-CYCLE6-FIX-DIST-20260906T021626Z) | 1 | 5527900 | 428 | 0659232d6c55ba274f2d0d2f0499bc72bd325369ce89ca3f95c0f33d95bd8a3b | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T011745Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE6-FIX-20260906T021626Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE7-FIX-20260906T033114Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE7-FIX-20260906T033114Z.zip | v3.0-rc1 interim (PRE-CYCLE7-FIX-20260906T033114Z) | 1 | 5540851 | 429 | 388056ac309ed6ba3ab3542f3b25b9002d2369289ffe41586e191e8aef729b32 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T021744Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE7-FIX-DIST-20260906T033114Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE7-FIX-DIST-20260906T033114Z.zip | v3.0-rc1 interim (PRE-CYCLE7-FIX-DIST-20260906T033114Z) | 1 | 5540851 | 429 | 388056ac309ed6ba3ab3542f3b25b9002d2369289ffe41586e191e8aef729b32 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T021744Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE7-FIX-20260906T033114Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE8-FIX-2026-09-06T0540Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE8-FIX-2026-09-06T0540Z.zip | v3.0-rc1 interim (PRE-CYCLE8-FIX-2026-09-06T0540Z) | 1 | 5556451 | 430 | f5576bc0a89b52edf0e3fa56f8cebaa07514955af961ab4eaf1b864a11f06c36 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T033114Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE8-FIX-DIST-2026-09-06T0540Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE8-FIX-DIST-2026-09-06T0540Z.zip | v3.0-rc1 interim (PRE-CYCLE8-FIX-DIST-2026-09-06T0540Z) | 1 | 5556451 | 430 | f5576bc0a89b52edf0e3fa56f8cebaa07514955af961ab4eaf1b864a11f06c36 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T033114Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE8-FIX-2026-09-06T0540Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE9-FIX-2026-09-06T0706Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE9-FIX-2026-09-06T0706Z.zip | v3.0-rc1 interim (PRE-CYCLE9-FIX-2026-09-06T0706Z) | 1 | 5575569 | 431 | c1572e8f2ff734c0c0e595e691f5576381b4aa582d3771eda95924156219fa75 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T054034Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.PRE-CYCLE9-FIX-DIST-2026-09-06T0706Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE9-FIX-DIST-2026-09-06T0706Z.zip | v3.0-rc1 interim (PRE-CYCLE9-FIX-DIST-2026-09-06T0706Z) | 1 | 5575569 | 431 | c1572e8f2ff734c0c0e595e691f5576381b4aa582d3771eda95924156219fa75 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260906T054034Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE9-FIX-2026-09-06T0706Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.STALE-dist2-2026-09-05T2253Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.STALE-dist2-2026-09-05T2253Z.zip | v3.0-rc1 interim (STALE-dist2-2026-09-05T2253Z) | 1 | 2210039 | 414 | 78f5b287f64b1253ddae76113383f8a223ccf4971d6cd237df8528ba09625940 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T193643Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.STALE-dist3-2026-09-05T2253Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.STALE-dist3-2026-09-05T2253Z.zip | v3.0-rc1 interim (STALE-dist3-2026-09-05T2253Z) | 1 | 2212133 | 414 | b46e0a05757eb2a48db42ef23a16a5684584eccf24725b91f9164f7bcb9f7107 | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T195137Z; |  | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed | not asserted (interim build)
deborah-research-assistant-v3.0-rc1.STALE-dist4-2026-09-05T2253Z.zip | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.STALE-dist4-2026-09-05T2253Z.zip | v3.0-rc1 interim (STALE-dist4-2026-09-05T2253Z) | 1 | 2213791 | 414 | f6200fd93df1adf7574de52332305017188763f04041ea27f1d9dde63c0c281d | deborah-research-engine-v3.0 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260905T200026Z; | v30/superseded_archives/deborah-research-assistant-v3.0-rc1.PRE-CYCLE2-FIX-2026-09-05T2000Z.zip | interim/superseded v3.0 audit-cycle build; identity from filename tag and RELEASE_METADATA only; not separately diffed; byte-identical duplicate | not asserted (interim build)
deborah-research-assistant-v3.1-rc1.zip | v31/dist/deborah-research-assistant-v3.1-rc1.zip | v3.1-rc1 | 1 | 5799591 | 449 | 84212ae9c0e185db6588bf246043ae37280dfd4ac4e6967685d645b519b7e652 | deborah-research-engine-v3.1 | True | 11 |  |  | release_candidate=1;build_id=rc1-20260909T224424Z; |  |  | PARTIAL: constant 3.1.0-dev
deborah-research-assistant-v3.2-rc1.zip | v32/dist/deborah-research-assistant-v3.2-rc1.zip | v3.2-rc1(c-161010Z-final) | 1 | 5851323 | 448 | 4fd4eb8f93b7c8d0ff4420cd75b5687e09add3d5e60fad96b25750bcf3717390 | deborah-research-engine-v3.2 | True | 0 |  |  | release_candidate=1;build_id=rc1-20260911T161010Z; |  | 0 TLS fixture pems (expected 11); omits 11 tls pems; embedded V32_UPGRADE_REPORT predates final inspection | PARTIAL: constant 3.2.0-dev
deborah-research-assistant-v3.2-rc2.zip | v32/dist_rc2/deborah-research-assistant-v3.2-rc2.zip | v3.2-rc2 | 2 | 5874995 | 460 | 3825930b4c2d40f3be8ce01db2a5af0d701a09a4c69fec0e95cbd2f23d041f42 | deborah-research-engine-v3.2 | True | 11 |  |  | release_candidate=2;build_id=rc2-20260911T220332Z; |  | __version__ 3.2.0-dev; README mentions rc1 only | PARTIAL: metadata rc2, constant 3.2.0-dev
deborah-research-assistant-v3.2-rc1.zip | v32/evidence/final test package Ω/deborah-research-assistant-v3.2-rc1.zip | v3.2-rc1(b-155618Z) | 1 | 5843714 | 447 | 1fcc8b0ea5838e4063a753c625ff4dae555b050ba63102be4b97334206c9b5d0 | deborah-research-engine-v3.2 | True | 0 |  |  | release_candidate=1;build_id=rc1-20260911T155618Z; |  | 0 TLS fixture pems (expected 11); omits 11 tls pems; embedded V32_UPGRADE_REPORT predates final inspection | PARTIAL: constant 3.2.0-dev
deborah-research-assistant-v3.2-rc1.zip | v32/evidence/test package Ω/deborah-research-assistant-v3.2-rc1.zip | v3.2-rc1(a-153938Z) | 1 | 5835362 | 446 | fe4c795345cf2b269e400f90a5740a9cb3246e38269c6629dce942911994e2c8 | deborah-research-engine-v3.2 | True | 0 |  |  | release_candidate=1;build_id=rc1-20260911T153938Z; |  | 0 TLS fixture pems (expected 11); omits 11 tls pems; embedded V32_UPGRADE_REPORT predates final inspection | PARTIAL: constant 3.2.0-dev

## Findings
finding_id | category | title | first_affected_version | discovered_in | severity | root_cause | fix_version | regression_test | failed_on_defective_version | survived_later_versions | recurred | status_at_latest | evidence
M1 | security | DNS-rebinding SSRF (resolve-then-connect gap) | v1.0 | v1.2 audit | high | URL host checked, socket resolved separately | v1.2 (app/net.py pinned socket) | tests/test_v12_regressions.py; fail_on_v11_demo.py | yes (18/18 VULNERABLE on v1.1) | yes | no | Resolved | AUDIT_LOG.md v1.2 audit; net.py _open_pinned_socket
M2 | security | No overall deadline on fetches | v1.0 | v1.2 audit | medium | No budget across redirects/reads | v1.2 | test_v12_regressions | yes | yes | no | Resolved | AUDIT_LOG.md
M3 | security | Unbounded result sets | v1.0 | v1.2 audit | medium | No caps | v1.2 (caps); scenario test outstanding at v2.0 | FINDINGS_RECONCILIATION: scenario test outstanding | partial | unknown | no | Evidence unavailable (scenario test never confirmed) | FINDINGS_RECONCILIATION.md
M4 | security | Markdown link injection in reports | v1.0 | v1.2 audit | medium | Unescaped source text | v1.2; reopened and re-closed v2.0 | test_v12_regressions; v2.0 tests | yes | yes | yes (reopened v2.0) | Resolved | FINDINGS_RECONCILIATION.md
M5 | security | Trusted-domain spoofing (suffix match) | v1.0 | v1.2 audit | high | Naive endswith on host | v1.2 (PSL); reopened/re-closed v2.0 | test_v12_regressions | yes | yes | yes (reopened v2.0) | Resolved | app/psl.py; FINDINGS_RECONCILIATION.md
M6 | security | ZIP central-directory amplification | v1.0 | v1.2 audit | medium | Trusting declared sizes | v1.2 | zip safety tests | yes | yes | no | Resolved | AUDIT_LOG.md
L7 | security | Bootstrap token in URLs/logs | v1.1 | v1.2 audit | low | Token as query param | v1.2/v2.0 (fragment #bs=) | - | n/a | yes | no | Resolved | webui.main() url f-string
P0-B | security | Scrapy TLS certificate verification disabled | v1.0 | v2.0 Phase 0 | high | Scrapy default DOWNLOAD_VERIFY_CERTIFICATES=False never overridden | v2.0 Phase 0 | test in v2.0 suite (settings assertion) | yes | yes | no | Resolved (code-confirmed: setting absent v1.0-v1.2, True from v2.0) | app/crawler/settings.py per version
P0-C/P0.D4 | platform | Windows UTF-8 failure misdiagnosed (real cause: printing Unicode to cp1252 console) | v1.0 | v2.0 Phase 0 | medium | Console encoding, not file encoding | v2.0 Phase 0 (app/console.py) | test_v20_windows_gate | yes | recurred as W1 | yes | Resolved (W1 recurrence fixed RC2) | FINDINGS_RECONCILIATION.md; webui.main() configure_stdio
P0.D2 | platform | colorama missing from Windows wheel set (clean install fails) | v1.2 | v2.0 Phase 0 | medium | Wheel set built on Linux | v2.0 Phase 0 | - | yes | unknown | no | Resolved (claim) | FINDINGS_RECONCILIATION.md
P0.D3 | platform | SyntaxError on Python 3.11 (v1.2 '211 tests' never true on 3.11) | v1.2 | v2.0 Phase 0 | medium | 3.12-only syntax | v2.0 Phase 0 | 4-interpreter matrix (claim) | yes | yes | no | Resolved (claim; no log) | FINDINGS_RECONCILIATION.md
N9 | security | Ambient proxy environment honoured | v1.2/v2.0 | v2.0 reconciliation | medium | urllib default opener | v2.0 RCs (app/net.py) | net tests | yes | yes | no | Resolved (code-confirmed) | app/net.py docstring line 18
N10 | testing | TLS negative fixtures missing | v2.0 | v2.0 reconciliation | low | No invalid-cert pems | v2.0-rc1 (11 pems) | cert-rejection tests | n/a | omitted from v3.2-rc1 zip | yes (v3.2-rc1) | Resolved in v3.2-rc2 (pems restored) | manifest tls_fixture_pems
W1 | platform | 51 encoding-less text operations in tests/scripts/kit | v2.0-rc1 | v2.0 RC1 Windows | medium | open()/subprocess without encoding | v2.0-rc2 | test_v20_windows_gate::test_w1_every_text_operation_states_its_encoding | yes | recurred v3.2-rc1 (test_v32_sdk.py:67) | yes | Resolved in v3.2-rc2 | UPGRADE_REPORT blocked failures; RC2_REPORT blocker 5
W2 | platform | 100k-char node ID exceeds 32,767 env limit on Windows | v2.0-rc1 | v2.0 RC1 Windows | medium | Environment-passed identifier | v2.0-rc2 | test w2 | yes | yes | no | Resolved | AUDIT_LOG.md W1-W5
W3-v20 | platform | Non-ASCII, LF-only batch files | v2.0-rc1 | v2.0 RC1 Windows | low | cmd.exe encoding | v2.0-rc2 | batch tests | yes | yes | no | Resolved | AUDIT_LOG.md
W5-v20 | testing | Kit diagnostics flood truncates failing test ID | v2.0-rc1 | v2.0 RC1 Windows | medium | 2000-char detail dominated by repeated 'a' | v2.0-rc2 | kit tests | yes (JSON G5 detail) | yes | no | Resolved | uploaded windows_acceptance_result.json (rc1)
W6-W9 | platform | Launcher started legacy v1.2 app.webapp:8756; G8 static-only -> RC2 Windows pass was a false positive | v2.0-rc1 | v2.0 RC2 Windows (owner) | high | Launcher never updated for v2 entry point | v2.0-rc3 (app.interfaces.webui:8758) | G8 runtime gate | yes | yes | no | Resolved (code-confirmed rc1/rc2 vs rc3 bat) | zip members Start_Deborah_Research_Assistant.bat
V1-V4 | testing | Kit defects: Unix-only browser fixture; zip trusted by filename; G10 blamed product for pre-existing listener; wrapper used Python 3.14 | v2.0-rc1 | v2.0 RC3 Windows | medium | Kit assumptions | v2.0-rc4 | kit tests; RELEASE_METADATA identity | yes | RC4 never run on Windows | no | Resolved (unverified on Windows) | turn_0048; RELEASE_METADATA notes
A-RC4-1 | functional | CLI start killed the run it started | v2.0-rc1 | v2.0 RC4 audit | high | Process lifecycle | v2.1-rc1 | cli tests | yes | yes | no | Resolved | AUDIT_LOG.md RC4 audit
A-RC4-2 | functional | No HTML report despite README claim | v2.0-rc1 | v2.0 RC4 audit | medium | Renderer not wired | v2.1-rc1 | report tests | yes | yes | no | Resolved | AUDIT_LOG.md
A-RC4-3..6 | functional | Resume-skills parse; foundation playbook unreachable; comparison silent drops; stale ledger | v2.0-rc1 | v2.0 RC4 audit | medium | various | v2.1-rc1 | various | yes | yes | no | Resolved (claim) | AUDIT_LOG.md
A-V21-1 | packaging | Nested release archive inside rc4 zip (b embeds a) | v2.0-rc4 | v2.1 audit | medium | build_release_zip ran inside dist dir | v2.1-rc1 | test_v21_packaging (stray archives) | yes (manifest confirms 348 vs 347) | yes | no | Resolved | archive_manifest_raw.csv
J-V21-1 | functional | Prompt-injection flags not rendered in report | v2.0 | v2.1 audit | medium | Renderer omission | v2.1/v2.2 | render tests | yes | yes | no | Resolved (claim) | AUDIT_LOG.md
C3-NEW-1 | identity | v2.2 archive shipped stale __version__ 2.1.0 and a test pinned to the stale literal (owner saw v2.1.0 on Windows) | v2.2 (953d7cc4) | v2.2 audit cycle 3 | medium | Constant not bumped; test asserted wrong literal | v2.2-rc1 rebuild c10c1722 | test_version_is_v2 corrected | yes | yes | no | Resolved (rebuilt archive not re-run on Windows) | AUDIT_LOG.md cycle 3; comparison version_constant
B-1 | security | Consent approval not bound to research depth (quick approval starts deep run) | v3.0 dev | v3.0 audit cycle 1 | high | Approval token lacked depth binding | v3.0-rc1 (cycle 1 fix) | cycle-1 regression test | yes | yes | no | Resolved | v30/AUDIT_CYCLE_1.md webui.py:801-816
C10-1 | reliability | Descriptor/connection leak | v3.0 dev | cycle 10 | medium | Unclosed sockets | cycle 10 fix | test | yes | yes | no | Resolved | v30/AUDIT_CYCLE_10.md
M17-1/M17-2 | ux-honesty | Non-ASCII batch filenames refused with false diagnosis; retention-deleted runs still listed as Finished | v3.0-rc1 | cycle 17 | low | Wording/ state | cycle 17 fix report | tests | yes | yes | no | Resolved | v30/AUDIT_CYCLE_17.md; CYCLE_17_FIX_REPORT.md
W3/W4-v30 | platform | Concurrent export PermissionError on Windows (xlsx/json burst) | v3.0-rc1 | v3.0 RC1 Windows JSON | high | Open file handles during rename on Windows | v3.0-rc2 | tests/test_v30_rc2_w3*.py, w4 | yes (junit 5F) | Windows never re-run | unknown | Resolved on Linux only; Windows unverified | uploaded eed77b4f.../acceptance_junit.xml; RC2_FIX_REPORT
W5-v30 | testing | SBOM test machine-dependent | v3.0-rc1 | v3.0 RC1 Windows | low | Environment coupling | v3.0-rc2 | w5 test | yes | Windows never re-run | unknown | Resolved on Linux only | RC2_FIX_REPORT.md
W6-v30 | testing | test_v30_screen_timestamps 7 errors on Windows | v3.0-rc1 | v3.0 RC1 Windows | low | Timestamp/locale assumptions | v3.0-rc2 | w6 test | yes | Windows never re-run | unknown | Resolved on Linux only | junit
W7-v30 | security | chmod no-op on Windows (keys/DB not restricted) | v2.0 | v3.0 RC1 Windows | medium | POSIX-only permission call | v3.0-rc2 (icacls) | w7 test (mocked on Linux) | yes | Windows never re-run | unknown | Resolved on paper; Windows unverified | RC2_FIX_REPORT.md; WINDOWS_FINDINGS_RECONCILIATION.md
W8-v30 | ux/security | Consent dialog always painted (body.spa .modal-backdrop{display:flex} outranked UA [hidden]) | v3.0-rc1 | v3.0 RC1 Windows screenshot | high | CSS specificity | v3.0-rc2 (_HIDDEN_RULE + import-time assert) | jsdom test | yes | no real-browser evidence after fix | unknown | Fix jsdom-tested only; real-browser Not verified | webui.py:1079; RC2_FIX_REPORT
A-RC2-1 | packaging | RC2 fix report missing from zip | v3.0-rc2 | RC2 audit cycle 1 | low | Build exclusion | v3.0-rc2 rebuild | packaging test | yes | yes | no | Resolved | v30/rc2_dev/RC2_AUDIT_CYCLE_1.md
A-RC2-2 | testing | 300 s budget wall-clock coupling (one failure under two concurrent suites) | v3.0-rc2 | RC2 audit cycle 2 | low | Time budget coupled to CPU availability | budget raised (fix shipped un-audited); residual seen v3.1 | test_v22_scenarios::test_keyless_foundation_run_reaches_propublica_and_labels_figures | yes | residual failure reproduced v3.1 concurrent runs | yes | Unresolved (residual coupling recorded, not fixed) | V31_FEATURE_REPORT.md 'One observation'
V31-MODEL | functional | Shipped default Gemini model gemini-2.0-flash retired (HTTP 404) | v3.1-rc1 dev | v3.1 live smoke 2026-09-09 | medium | Stale model id | v3.1-rc1 (gemini-3.6-flash) | test pin updated | yes | yes | no | Resolved (1 live call) | V31_FEATURE_REPORT.md addendum; geminiextract.py DEFAULT_MODEL
V31-OUTPUT | output-quality | Real Hewlett report (2026-09-11) lists journal DOIs as findings; no EIN, no website, no filings | v2.0 (general research path) | this audit (uploaded PDF) | high | Entity-agnostic web/scholarly providers admitted as findings | v3.2 nonprofit pipeline does not replace general path | none | n/a | unknown for general path in v3.2 | unknown | Unresolved (general research path unverified in v3.2) | uploaded William-Flora-Hewlett-Foundation-research-report-2026-09-11.pdf
V32-R1-404 | functional | ProPublica name search 404: '&' rewritten to 'and' | v3.2-rc1 | v3.2 rc1 live acceptance | high | Query rewrite | v3.2-rc2 (as-typed %26 + bounded phrasings) | tests/test_v32_rc2_repair.py | yes | yes | no | Resolved (live 200, EIN 941655673) | nonprofit.py:621-650; RC2_REPORT
V32-R1-PEM | packaging | Final rc1 zip omitted 11 TLS fixture pems; reported suites ran source tree not zip | v3.2-rc1 | v3.2 rc1 final inspection | medium | Blanket .pem exclusion | v3.2-rc2 | packaging test | yes | yes | no | Resolved (manifest: 11 pems in rc2) | UPGRADE_REPORT 'Final package blocker'; manifest
V32-R1-BRAVE | testing | Brave free_allowance wording test failed | v3.2-rc1 | final_suite | low | Wording drift | v3.2-rc2 | test_v30_providersettings | yes | yes | no | Resolved | final_suite.log
V32-R2-XML403 | functional | All 12 ProPublica 990 XML downloads 403 (Cloudflare challenge); no entity lock; RESEARCH INCOMPLETE | v3.0 (propublica provider) | v3.2 rc2 live acceptance | high | Upstream bot challenge; no direct apps.irs.gov per-object XML route | none | none | n/a | open | n/a | Unresolved | live_acceptance_rc2.json; provider_table_rc2.md
V32-R2-IRSTO | functional | IRS EO BMF eo_ca.csv and 2025 index timed out during body; 2026 index (47.5 MB) had no usable object id | v3.2-rc2 | v3.2 rc2 live acceptance | high | Body deadline vs bulk file size | none | none | n/a | open | n/a | Unresolved | provider_table_rc2.md
V32-R2-IDENT | identity | rc2 archive keeps __version__ 3.2.0-dev and README mentions rc1 only while RELEASE_METADATA says rc2 | v3.2-rc1 | this audit (comparison) | low | Constant/README not stamped | none | none | n/a | open | n/a | Unresolved | comparison.json version_constant; rc2 README
WIN-OUTSTANDING | platform | No Windows execution of any build after v3.0-rc1 (rc2, v3.1, v3.2 rc1/rc2) | v3.0-rc2 | cumulative | high | Owner re-acceptance never run | none | none | n/a | open | n/a | Unresolved (WINDOWS RE-ACCEPTANCE REQUIRED) | RC2_REPORT.md; RELEASE_METADATA notes

## Output quality
version | observation | assessment | evidence
v1.2 | 6 generated reports shipped inside the zip (data/ and reports/) | Demo/self-run output; content not assessed for correctness | Evidence: archive members
v2.0-rc4 | No HTML report produced despite README (A-RC4-2) | Failed | AUDIT_LOG.md RC4 audit
v2.2 | Plain-text report, job-id UX, no persistence (AUDIT_V3 ten problems) | Poor usability per project's own audit | AUDIT_V3.md 2026-09-04
v3.0-rc1 | MINOR-1 cycle 6 financial table overflow in PDF; cycle 7 MAJOR export path defect | Fixed during cycles | v30/AUDIT_CYCLE_6.md, _7.md
v3.1 | Real Hewlett report 2026-09-11: 6 pages, 7 pages read from 6 domains, 28 statements; findings are journal DOIs (10.1002/cac2.12426, 10.1007/s00125-024-06200-w); 0 EIN mentions, 0 hewlett.org, 990 mentioned 3x (boilerplate) | Failed (normal-looking but wrong) | uploaded PDF (independent evidence)
v3.2-rc1 | Four formats saved; verdict RESEARCH INCOMPLETE; no identity, no filings | Failed but honest | v32/deliverables/*after.*
v3.2-rc2 | Four formats saved; RESEARCH INCOMPLETE; provisional candidate EIN 941655673 labelled; 0 financial years; 0 reconciliations; full request log | Failed but honest; disclosure quality improved | v32/deliverables_rc2/*rc2.*

## Open gaps
priority | gap | impact | evidence
1 | Authoritative Form 990 XML retrieval fails live (ProPublica 403 Cloudflare; no direct IRS per-object route) | Blocks entity lock and every financial figure | v3.2-rc2 live_acceptance_rc2.json
2 | IRS bulk fallback (EO BMF CSV, annual index) times out during body from the sandbox | Fallback never succeeded live | provider_table_rc2.md
3 | No Windows execution of any build since v3.0-rc1; W1-W9 fixes, icacls, consent-dialog CSS verified only on Linux/jsdom | Windows status unknown for v3.0-rc2 .. v3.2-rc2 | RC2_REPORT.md; RELEASE_METADATA notes
4 | General research path admits entity-unrelated scholarly/DOI content as findings (v3.1 Hewlett PDF); v3.2 nonprofit pipeline is a separate branch | Reports can look complete while being wrong | uploaded PDF
5 | Release identity inconsistency in latest archive (__version__ 3.2.0-dev; README rc1-only; metadata rc2) and A-RC2-2 residual timing coupling | Identity/repeatability | comparison.json; V31_FEATURE_REPORT

## Claims vs evidence
claim | where_claimed | evidence | verdict
v1.2 passes 211 tests on Python 3.11-3.14 | v1.2 README/AUDIT_LOG | P0.D3: SyntaxError on 3.11; never ran on 3.11 | Contradicted
v1.2 archive is version 1.2 | zip name / README | app/__init__.py still 1.1.0 | Contradicted
v1.x crawler fetches over verified TLS | v1.x security docs | Scrapy DOWNLOAD_VERIFY_CERTIFICATES default False, not set in v1.0-v1.2 settings.py (code-confirmed); P0-B | Contradicted
v1.2 Windows failure caused by UTF-8 file handling | v1.2 notes | Real cause console cp1252 (P0-C/P0.D4) | Contradicted
v1.2 installs cleanly on Windows from wheel set | v1.2 handoff | colorama missing (P0.D2) | Contradicted
v2.0 RC2 passed all nine Windows gates (all_pass true) | AUDIT_LOG / owner run | Launcher started legacy app.webapp:8756 (rc1/rc2 .bat code-confirmed); G8 static-only; W6-W9 | Contradicted (false positive)
v2.0 Phase 0 fixed Windows encoding | FINDINGS_RECONCILIATION | W1: 51 encoding-less operations found in RC1 on Windows; recurred again v3.2-rc1 | Contradicted (recurred)
v2.0 RC3 kit: G10 failure is a product defect | RC3 kit output | V3: pre-existing listener on the machine | Contradicted
v2.0 RC3 kit verifies the archive it tests | kit design | V2: zip trusted by filename | Contradicted
v2.0 RC4 is a Windows-accepted baseline | v2.1 PROJECT_STATUS | Same document: RC4 has NOT been run on Windows | Contradicted (self-contradiction)
v2.0 RC4 archive contains only the release tree | RELEASE_METADATA expected_file_count 348 | Member --help/deborah-research-assistant-v2.0-rc4.zip embedded (A-V21-1) | Contradicted
v2.0 CLI can start a research run | README/CLI docs | A-RC4-1 start killed the run | Contradicted (fixed v2.1)
v2.0 produces an HTML report | README | A-RC4-2 no HTML report | Contradicted (fixed v2.1)
v2.0 transport ignores ambient proxies | v2.0 security docs | N9 OPEN at reconciliation; fixed later in app/net.py | Contradicted at the time
v2.2 archive is v2.2 | zip/README | Superseded build shipped __version__ 2.1.0; owner saw v2.1.0 on Windows; test pinned stale literal | Contradicted (rebuilt)
v3.0 consent approval binds the requested run | v3.0 design/TEST_PLAN | B-1: quick approval started deep run | Contradicted (fixed cycle 1)
v3.0 restricts key/DB file permissions | SECURITY_AND_PRIVACY | W7: chmod no-op on Windows | Contradicted on Windows (icacls fix unverified)
v3.0 consent dialog hidden until needed | TEST_PLAN row (jsdom pass) | Windows screenshot: dialog always painted (W8) | Contradicted (fix jsdom-only)
v3.0-rc2 zip contains the RC2 fix report | RC2 handoff | A-RC2-1 missing from zip | Contradicted (rebuilt)
v3.1 default Gemini model is available | v3.1 docs/PROVIDER_SETUP | gemini-2.0-flash retired (HTTP 404) at first live call | Contradicted (changed)
v3.1 report 'states what the sources said' about the researched organization | report boilerplate (uploaded PDF) | Findings are unrelated journal DOIs; no EIN/website/filings | Contradicted
v3.2-rc1 embedded V32_UPGRADE_REPORT: suite results reproduce from the archive | in-archive report | Final zip omitted 11 pems; suites ran source tree (external addendum) | Contradicted (self-identified)
v3.2-rc1 ProPublica name search reaches the organisation | rc1 design | HTTP 404 after '&'->'and' rewrite | Contradicted (fixed rc2)
v3.2-rc2 archive identity is rc2 | RELEASE_METADATA | __version__ 3.2.0-dev; README mentions rc1 only | Contradicted (unresolved)
v3.0-rc2 suite 4308/0/0/0 on 3.13 and 3.14 | RC2_FIX_REPORT | Logs written to /tmp, not supplied | Evidence unavailable (not contradicted)
v3.0-rc1 Linux 4191/0/0 | AUDIT_CYCLE_18, HANDOFF | Consistent with Windows junit total 4191; Linux log not supplied | Supported by consistent counts; log unavailable
v3.2-rc2 packaged suite 4426/0/0/0 | RC2_REPORT | packaged_suite_rc2_junit.xml supplied | Supported (machine-readable, Linux only)
v3.2-rc2 ampersand fix works live | RC2_REPORT | live_acceptance_rc2.json search 200, EIN 941655673 | Supported